## Sheet1
Feature | Tasks | Time Cost (in hours) | Time spent | Notes
Inline nav (About Page)
| Research examples | 2 | 4.25 | Research mobile applications; Ask Jesse for advice; Determine PRL-appropriate structure; Design XD mockup; Maybe ask Federica for opinion
| Codepen experiment | 5 | 8 | DONE
| Accessibility check | 1 | 4 | Upload to Code pen at this point; extra time spent debugging on browsers…
| Test on Mura | 2 | 4
| Update About page | 0.5 | 0.5
News story progress bar | Research | 2 | 0.5 | Determine if needed at all
| Design | 3 | 3
| Accessibility check | 1 | 0
| Test on Mura | 2 | 2
| Implement | 1 | 0.5 | Includes cross browser testing
About Page changes
| Smaller hero? | 0.5 | 0.25
| Remove BES # | 0.25 | 0.1
Prominent findings page
| Decide on content and website placement | 4 | 1hr20mins | Touched base with Christoph - will place on About Us page under Brief History
| Research format | 1.25 | 50 mins | A Zoom Timeline is too clunky. Form will be determined by the content.
| Write copy | 1.5
| Decide on image assets | 0.75
| Test and Design API endpoints | 3 | 3 | Sciwheel API works well. EndNote doesn't work. Took much longer to implement than 3 hours…
| Design timeline | 3 | 30mins | Rotating list through JS function
| Test on Mura | 2
| Add to About page | 1
For the public' page
| Decide on content and placement | 4
| Create copy | 2
| Copy revisions | 1
| Collect/produce assets | 3
| Codepen mockup | 2
| Test on Mura | 1.5 |  | Include accessibility
| Publish | 1
Images of People |  |  |  | Prepare but postpone application. Due to COVID, MSU is asking for iages of people with PPE
| Determine pages that need to be changed | 0.5
| Collect/produce assets | 2
| Update pages | 1
TOTAL TIME |  | 54.75