## Sheet1
Feature | Tasks | Time Cost (in hours) | Time spent | Notes
Inline nav (About Page)
| Research examples | 2 | 4hr15min | Research mobile applications; Ask Jesse for advice; Determine PRL-appropriate structure; Design XD mockup; Maybe ask Federica for opinion
| Codepen experiment | 5 | 8hr | DONE
| Accessibility check | 1 | 1.75 | Upload to Code pen at this point
| Test on Mura | 2 | 3
| Update About page | 0.5
News story progress bar | Research | 2 |  | Determine if needed at all
| Codepen design | 3
| Accessibility check | 1
| Test on Mura | 2
| Implement | 1
About Page changes
| Smaller hero? | 0.5
| Remove BES # | 0.25
Prominent findings page
| Decide on content and website placement | 3 |  | Touch base with Christoph
| Explore Zoom timelines | 0.5
| Timeline copy | 1.5
| Timeline image assets | 2
| Design timeline | 1.5
| Test on Mura | 2
| Create page | 1
For the public' page
| Decide on content and placement | 4
| Create copy | 2
| Copy revisions | 1
| Collect/produce assets | 3
| Codepen mockup | 2
| Test on Mura | 1.5 |  | Include accessibility
| Publish | 1
Images of People
| Determine pages that need to be changed | 0.5
| Collect/produce assets | 2
| Update pages | 1
TOTAL TIME |  | 49.75